***** G.C. to pay $720 to pull LDP Permit from city of Thomasville

***** G.C. to pay $13,335.59 to pull Building Permit from Thomas County.  or RT to issue check and mail to P.O. Box 1173 Thomasville GA 31799 via UPS, OR 227 West Jefferson St. Thomasville GA 31792 via FED EX.

***** BLDG refresh set has not been submitted to the city for review pending permit being pulled but the city is aware of upcoming changes.

***** Civil revision incorporating CRM comments is in process and will be resubmitted after LDP permit has been pulled.

*****One existing wooden pole along HWY 84 at proposed new driveway needs to be relocated 100ft east. it is a GDOT pole for traffic signal fiber line.   pending GDOT relocation plans to get price.

Real Estate/Site:

- RaceTrac, Inc. owns 5.5 acres undeveloped land at the signalized intersection of HWY84 & GA3 (Old Albany) in Thomas County GA – plat is recorded with the county.

- Site has one full access and one RI-RO on GA SR3 (Old Albany Rd) plus one RI-RO on HWY 84, all are within GDOT ROW

- RW EDO with 8 front MPDs doble row and 3 Diesel fueling positions

- 22 auto parking, no truck parking, FFE 244ft

- Shared front and diesel tank pit and one 2 bay dumpster

- Two above ground stormwater detention ponds

- No wetlands on this site

Easements

- Existing 15ft general Utility easement on GA SR3 frontage.

- Tree Removal Easement Area (Visibility Area) northwest onto adjacent property, recorded

- Access Easement on both HWY 84 as well as GA SR3, recorded

- Slope Easement along southern and western property boundaries, recorded

Environmental

- Soil

  - There were no environmental issues, No remediation is required, soil can be used onsite and offsite.

  - Landfill account to be set up with Thomasville Solid Waste department. Solid Waste & Landfill  (229) 227-7037. $30-$40 cost per ton for disposal of C&D does not include transportation. Tree disposal accepted however fee depends on diameter of the tree. Soil disposal requires to be tested for chemicals prior to taking to landfill

- Ground water

  - Ground water was not encountered.

- Dewatering restrictions

  - Dewater onsite requires county approval, and permit is needed

  - Pricing: Cost per gallon for disposal $0.18/gallon does not include transportation.

  - No remediation required

Geotech

- Universal (Contour Engineering) conducted the Geotech investigation.

- There were no auger refusals in the 12 borings including the proposed pond areas

- As far as using the excavated materials at stormwater pond areas, the top 5 feet was a high plasticity clay. That won’t be good for structural fill, but it can be mixed with a sandier material and as long as the liquid limit and plasticity limit of the blended soil is tested to be above 40 and 20, respectively.

- Excavated materials at the pond areas, can be used in landscape areas and to overbuild slopes on site.

Engineering: Rowshi Craven

- Utilities Connections and /Relocations:

  - Power - Electrical service is provided by Thomasville Utilities, proposed connection is to an existing power pole on Old Albany on the same side as our full access driveway.

Power easement for secondary run to be coordinated onsite after primary route is finalized at precon.

  - Water - water tap is to existing water line on Old Albany rd. Water meter and back flow preventer to be installed by City of Thomasville. Fees to be paid by RT.

  - Sanitary Sewer - with City of Thomasville.  Force Main tap is off of Old Albany Rd across the street.  A pump station with a grinder is needed in order to connect into the existing sewer force main.

  - Sewer line from back of the building bypasses the grease trap then connects to sewer line

  - City of Thomasville Sewer dept will perform jack and bore and install tap after RT pays $25355.25  includes the below items and department review fees:

    - Fire Hydrant Assembly install

    - 2” Water meter install

    - 2” water BFP install

    - FM BFP install

    - FM Valve install

    - FM Tap install

    - FM Jack and Bore install

  - Stormwater is with City of Thomasville. All stormwater inlets will drain to two on-site above ground ponds one by the EDO canopy and one behind the store.  Both ponds will be fenced and gated.  A water quality unit is provided for drainage into the outfall area located by the access drive on Old Albany rd.

  - Two ACO 40Lft + 33Lft aquaduct 8” trenches at access drives off of Old Albany rd. vendor estimate is provided in cost estimate sheet.

  - Telephone - Telecommunication service is provided by CNSNEXT from the existing overhead cables along Old Albany Rd by our full access drive.

  - Gas service capacity is not available for our location. Gas is City of Thomasville.

Building / Canopy / Signage:

- Building : RW stick build prototype. (Refresh received 2/9/23 but not submitted yet)

  - Building is not sprinkled.

- Auto Canopy: Single column, Double row, total eight (8) MPDs,

  - No cladding, downspouts on the columns closest to the building and piped into the storm water management system

- Diesel Canopy: 3 lane, 4 MPD

  - No cladding, downspouts and piped into the storm water management system. Per RaceTrac spec, the EDO lanes will be drained by center drains going to one 1000-gallon OWS.

- Dumpster: 2 bay No Roof with storage.

- Signage:

  - 1 - RaceWay parallelogram on building, Raceway Standard Logo-80 SF.

  - 1 - Banner sign on the building, On the GO 40 SF.

  - 2 - RaceWay pole mounted price signs, 150 SF, 30FT Height to top of cabinet

  - 1 – Auto canopy Cloud sign, 30 SF

  - 1 – Diesel Canopy Cloud sign + exit only,

  - 4 - Directionals @ 8ft tall

- Permits:

  - Demolition: The site is undeveloped and requires site clearing and tree removal – burning permit only available during certain months following restrictions by the city through Thomasville Fire Rescue Department, (229) 227-4099.

  - Utility ROW: Relocate one pole on

  - GDOT: GDOT permit A-275-008985-4. Please contact Michael Sumner to set up a pre-con and give him the Bond and have 2 sets of drawings and receive GDOT permit prior to starting any work.  Have 2 copies of GDOT set of drawings on site at all times.

  - LDP: The LDP approved by Thomasville.   The contractor will need to pay a $720 permit fee to pull the permit.

  - Building: Building plans are approved by Thomas County. Formal permit won’t be issued until fees are paid by G.C.

  - Canopy: Canopy plans have been approved by the building department with the building plans. Canopy columns do not require cladding for either front or back canopy.

  - Tanks: Tank Plans approved by SFM, Permit No.SS22-000481,

  - Signage: in review with Thomas county via vendor Anchor.

  - NOI: Erosion control approved, Permitee GAR189DA7-V1

  - NPDES: State watershed approval by Department of Natural Resources EPD, Permit No. GAR100001, File SW-136-00-178

- Pre-Construction:

  - Pre-construction meeting will need to be scheduled with:

    - City of Thomasville –

City of Thomasville ROW superintendent, Curtis Crocker, (229)227-7095

    - State Fire Marshal (Tanks)

      - Jason Pritchett, 404-357-4340, jpritchett@sfm.ga.gov

    - GDOT Permit Inspector –

      - Michael Sumner, 229-309-0225, msumner@dot.ga.gov

    - Thomasville Electric -

- Bonds:  GDOT Bond for work in ROW $30,000 –

- Construction Budget:

  - ACO Trench drains = $7,320.00 + $2,500.00 Freight = $9,820

  - Wascon Grinder Pump Station = $15,240.84 (931-823-1388 * Cell 931 349 0441 * jonathanc@wasconinc.com * www.wasconinc.com)

  - Thomasville Water and Sewer Tap Fee: $25,355.25

  - Thomas County Building Permit Fee = $13,335.59

  - Thomasville LDP Permit Fee = $720